PickSell Project Audit

Web, mobile and all roles. Audit only: no code, data or configuration was changed.

Date: 2026-10-28.   Scope: Picksell (Laravel web, logistics portal, rider API), Pickrush rider app (Flutter), Picksell buyer app (Flutter).

## Checks run

- php artisan test (in-memory SQLite): 418 of 418 passed.

- Rider app flutter test: 11 of 11 passed. flutter analyze: info-level notes only (8 on rider app, 1 on buyer app).

- Buyer app has one test, the default Flutter counter test, which is stale.

- Not inspected: most Blade view markup (web UI polish unassessed). No app was driven on a device.

# A. Project completion snapshot

| Area | Status | Note |
| --- | --- | --- |
| Web app (Buyer, Seller, Admin) | Partially complete, strong | Real workflows with permissions, audit log and 400+ tests. |
| Logistics Company role | Solid foundation | The Pickrush portal: HQ, province-hub and station staff roles. |
| Buyer mobile app | Not implemented as a working app | UI plus a disconnected backend (see section D1). |
| Rider mobile app | Partially complete | Core pickup and delivery flow is connected, with gaps. |
| Backend and database | Solid foundation | Marketplace and logistics are solid. Buyer mobile auth and push are missing. |
| Cross-role integration | Partially complete | Order-to-parcel-to-order sync works forward. Returns and payments have gaps. |
| Overall maturity | Web and logistics near feature-complete for COD | Mobile is the weak side. |

# B. Solid foundations

- Marketplace and logistics core. The order lifecycle is a guarded state machine (OrderLifecycleService). The seller hand-over books a Pickrush parcel (PicksellBridge::book) and scans sync back to the order (SyncOrderWithParcel). Admin cancel is guarded by PicksellBridge::cancel. The parcel state machine (ParcelStatus) is in place.

- Logistics portal. HQ, province and station portals cover receiving, sorting, trips, dispatch, failed deliveries, cash and remittance, and rider onboarding.

- Rider API. Registration with email code, approval, login, batches, pickup, load, deliver, fail and earnings, with idempotent request keys.

- Access control and audit. Admin permissions, audit logging and ownership checks on rider calls.

- Tests. 418 backend tests pass, including Pickrush/EndToEndTest and PicksellBridgeTest.

# C. Remaining work

Priorities: P0 critical, P1 high, P2 medium, P3 low.

| Pri | Feature | Apps | Current state, remaining work, blocker | Evidence |
| --- | --- | --- | --- | --- |
| P0 | Buyer mobile backend and auth | Buyer app, backend | The app calls /api/register, /api/login, /api/upload-id and /api/chat/*. None exist in routes/api.php and there is no Sanctum. Remaining: build a token-authenticated buyer API (auth, products, cart, checkout, orders, chat, notifications). Blocker: decide native app or web only. | picksell/lib/services/auth_service.dart; routes/api.php |
| P0 | Buyer app checkout and orders | Buyer app | Cart is an in-memory list, notifications use sample data, no order or tracking screen. Remaining: real checkout, order list, tracking and notifications from the API. Blocker: the item above. | cart_service.dart; notifications_page.dart |
| P0 | Payments | Web, backend | No gateway and no payment method/status on orders. PicksellBridge::book sets cod_amount = order amount, so every parcel is treated as COD. Remaining: payment field per order and online payment (or confirm COD-only); book prepaid parcels with cod_amount 0. Blocker: business decision. | PicksellBridge.php; no payment_* in migrations |
| P1 | Push notifications | Rider, Buyer, backend | Rider app polls every 20 s while open. Code states FCM is not set up. Remaining: FCM tokens, server sends, tap-to-open. | assignment_watcher.dart |
| P1 | Proof of delivery policy | Rider, backend, Buyer | Proof is waybill scan + live photo + exact COD. No delivery OTP. Remaining: decide on the OTP; if yes, build it in API, rider app and buyer view. Blocker: decision. | DeliveryRoutes::deliver |
| P1 | Buyer returns through logistics | Web, backend | ReturnRequest and refunds work on the web, but no reverse parcel is booked in Pickrush. Remaining: book a return pickup for approved returns and feed the result back. Blocker: who ships returns. | BuyerReturnRequestController; AdminReturnController |
| P1 | Rider availability and location | Rider, backend | Online is only a flag. Logout leaves the rider on_shift. No presence timeout; no location sent while Online. Remaining: off_duty on logout, heartbeat timeout, location while Online. | RiderHomeController::shift; RiderAuthController::logout |
| P1 | Rider pay rates | Rider, backend | Rates are 15 per pickup and 35 per delivery, marked as placeholders. Remaining: set real rates. Blocker: business decision. | config/pickrush.php:68 |
| P2 | Rider profile management | Rider | Account screen is read-only; documents cannot be opened or replaced. Remaining: edit vehicle, re-upload documents with re-verification. | RiderProfile.php; account_screen.dart |
| P2 | Offer and job rules | Rider, backend | Offers never expire; a decline returns to staff (no auto next rider); no 3-job limit; no GPS on delivery. Remaining: add the rules you want, or document staff-led dispatch as the design. Blocker: decision. | RiderBatches::decline; deliver |
| P2 | Delivery history and COD detail | Rider | No history/filter screen and no per-order COD list. Remaining: history screen and COD order list. | earnings_screen.dart |
| P2 | Proof photo limits | Backend | Server accepts up to 8 MB plus heic/webp. Remaining: align with a 5 MB rule if wanted. | RiderBatchController |
| P2 | Refused delivery | Backend | "Buyer refused" counts as a normal attempt. Remaining: route straight to Return to Sender if that is the policy. Blocker: decision. | config failure_reasons |
| P3 | Mobile tests | Both Flutter apps | Buyer app has the default stale test; rider app has model tests only. Remaining: widget and integration tests. | picksell/test/widget_test.dart |
| P3 | Hardcoded buyer API URL | Buyer app | A stale ngrok URL is hardcoded. Remaining: move to configuration, as the rider app does. | ApiConfig.baseUrl |
| P3 | Offline sync | Rider | Offline is blocked with a message, which is acceptable. Remaining: optional queue and retry. | rider_task_service.dart |

# D. Cross-role and cross-app blockers

- Buyer app is disconnected from Laravel. It calls endpoints that do not exist and expects a bearer token. The web app uses session auth and has no Sanctum.

- COD is assumed everywhere. Seller, logistics and rider all treat the order amount as COD, because the order has no payment field.

- Return and refund flows stop at the web. Logistics never learns about an approved buyer return, so no rider is dispatched for it.

- Mobile cannot be notified in the background. With no push, a locked or closed phone cannot be told about a new offer.

- Status labels are mostly consistent. SyncOrderWithParcel::ORDER_STATUS maps parcel to order status correctly, and a sync failure is flagged to admins. No label/enum mismatch was found in the main path.

# E. Recommended completion order

| # | Phase | Objective and tasks | Acceptance condition |
| --- | --- | --- | --- |
| 1 | Decide scope | Choose the buyer channel (native app or web only), the payment model and the proof-of-delivery policy. | The three decisions are written down. |
| 2 | Payments and COD correctness | Add a payment field to the order; book prepaid parcels with cod_amount 0. | A prepaid order shows 0 COD in the rider app and in remittance. |
| 3 | Buyer API | Token auth and buyer endpoints, with tests. | A buyer can register, log in, see products and place an order from the app. |
| 4 | Buyer app wiring | Replace sample data and the local cart; add order tracking. | A mobile order appears in the seller portal and status updates reach the app. |
| 5 | Push notifications | FCM for rider offers and buyer updates. | A locked phone receives an offer and a delivery update. |
| 6 | Rider hardening | Fix logout, add presence, send location, set real rates, handle refused deliveries. | The earnings example matches your rate card. |
| 7 | Returns through logistics | Book return pickups for approved returns. | An approved return creates a rider task that completes the refund flow. |
| 8 | Polish | Rider profile editing, history, tests, config cleanup. | Backlog items P2 and P3 closed or consciously deferred. |

# F. Final audit verdict

## 1. Safe to retain

The order lifecycle, the Pickrush bridge, the parcel ledger, the logistics portal, the rider API and the permission model.

## 2. Five most important remaining tasks

- Buyer API and authentication.

- Buyer app checkout, orders and tracking.

- Payment model (prepaid vs COD).

- Push notifications.

- Returns booked through logistics.

## 3. First task

Make the scope decisions plus the payment model. Everything on the buyer side and the COD logic depends on them, so building screens first would cause rework.

## 4. Major unknowns

- Is the buyer channel meant to be the Flutter app or the web? The Flutter app looks abandoned.

- Is COD-only intended?

- The real rider pay rates.

- Whether the delivery OTP and the 60-second offer expiry in the test sheet are real requirements.

- On-screen behavior, permissions, camera and GPS are unverified because no app was driven on a device.